## Slide 1: Metro-Haul Project: WP6 Second Period Review
Old Dog Consulting (WP6 Leader)
Adrian Farrel
Old Dog Consulting

## Slide 2: Talking about WP6
Reminder
  What is WP6?
  What are the Deliverables and Goals?
Status and Resource Usage
Open Access : The big topic for WP6 at the moment
  What is it and what are we trying to achieve?
  What are we tracking?
  How are we doing?
Key Achievements in Year 2
Innovation Management – already covered in the morning
Issues and Next Steps

## Slide 3: Work Package 6 – Dissemination and Exploitation
What is WP6 Responsible for?
  Coordinate Dissemination Tasks
  Realise Open Knowledge Transfer
  Coordinate Publications and Workshops
  Coordination of Industry Whitepapers
WP6 KPIs Second Year (Versus Actual)
  Conference Contributions (Target was 10 in year two)
    Metro-Haul contributed >60 conference publications in the second year
  Journals and Papers (Target was 8 Academic journal articles in year two)
    Over 16 papers and journals articles have been published in the second year
  Contributions to SDOs, Open Source Project and related initiatives (Planned for >5 in year 2)
    Metro-Haul contributed to more than 12 specification and standards activities (IETF, ITU-T, BBF and MEF) and OpenSource (ONOS, OSM and OpenROADM)
  Industry panels and workshop involvement (Target was 1 in year 2)
    Metro-Haul developed and led 2 workshops in year 2 Co-located with NGON and EUCNC
  Definition of communication and exploitation plan (Year 2)
    Ongoing strategy and year 2 activities documented in “D6.2. METRO-HAUL Year2 report on communication, dissemination and standardisation activities”
  Industry Specification and Standards Contributions
  Coordinate Involvement in Open Source Projects
  Lead on Relationship with 5G-PPP

## Slide 4: WP6 – Tasks, Deliverables and Stretch Goals
WP6 Tasks (All 22 partners are involved in WP6, Lead by ODC)
  T6.1. Dissemination and Project Communication (Lead by UoB)
    Contributors: BT, TIM, CTTC, TID, UC3M, UNIVBRIS, UPC, CNIT, NAUDIT, OLC, LEX, ZN, HHI, TUE, CORIANT, TEI, ADVA, NBLF, ODC, STEC, NI
  T6.2 Exploitation, Standardisation (Lead by ODC), and Innovation Management (Lead by TIM)
    Contributors: BT, TIM, CTTC, TID, UNIVBRIS, NAUDIT, OLC, LEX, ZN, CORIANT, TEI, ADVA, NBLF, STEC, NI
WP6 Deliverables
  D6.1. Year1 report on communication, dissemination and standardisation activities (Complete in Year 1)
  D6.2. Year2 report on communication, dissemination and standardisation activities (Complete in Year 2)
    This document continues to summarize WP6 activities and achievements during the first year of the project, including:
    Updates to the project knowledge site
    Ongoing dissemination strategy plans for initial dissemination and exploitation plans
    The communication process amongst across the METRO-HAUL partners
    Documenting the standards effort across SDOs for METRO-HAUL work proposals
  D6.3. Final report on communication, dissemination and standardisation activities (Target for completion in Year 3)
Project Dissemination “Stretch Goals” before the end of the project:
  Development and publication of architecture at key Standards Development Organisation
    In progress
    See slides later for standardisation work
  Chapters in a book covering the Metro-Haul architecture and enabling technologies
    In progress
    See next slide
  Online tutorials for knowledge dissemination of enabling technologies

## Slide 5: Metro-Haul Book
  Filtered and filterless Metro networks
  Disaggregated optical nodes
  Optical transmission for metro networks
  Machine Learning for Optical Networks
  Control and management
  Monitoring and Data Analytics
  Autonomic Networking
  Service provisioning and slicing
  Demonstrations and applications for verticals
Typically, Metro-Haul is over-reaching
  Our stretch goal was “chapters in a book”
  We’re producing a whole book
Metro Networks: Where optics meet services
Luis Velasco, Filippo Cugini, Ramon Casellas (Eds.)
Table of Contents:
  Motivation: Toward 5G-ready optical metro networks
  Use cases and 5G-based services
  Services and architecture
  Metro reference scenarios
  Planning and techno-economics
WP2
WP3
WP5
WP4

## Slide 6: WP6 – Planned and Used Resources in Years 1 & 2
Graph shows cumulative resource usage against planned usage
Year 1 Conclusions
  WP6 under-used compared to plan by about 5PMs
  Some partners used resources faster than planned
  A few partners significantly under-used resources
Year 2 Conclusions
  Holding steady
  Year two resource usage almost exactly matched the plan
  Consequence is that WP6 is still about 5PM under plan
Year 2
Year 1

## Slide 7: What is Open Access and How to Track It?
Definitions
  Green: the author makes a copy available with some sort of permission from the publisher
  Gold: the publisher makes articles available for free (Note we don’t have any Gold OA)
There is a tension between OpenAccess and high-impact publications yielding a range of options…
  Open download from the publisher
  Open download from a stable public repository (OpenAire, Zenodo, ResearchGate)
  Open download from a stable private repository (University, Company, BSCW/pub)
  Open download from a transient private repository (Personal web site or personal pages at university)
  Copy on request (e.g., via ResearchGate)
Not all Disseminations are published (e.g., conference presentations), but they can still be made available
  Eurescom automatically adds Deliverables to Zenodo once they have been approved
Tracking of Open Access is in three places!
  SyGMa (was ECAS) shows the formal status of published dissemination
    It’s our report to the Commission used to show location of OA copies according to EC definitions
  The Eurescom Document Tracker is how we track all documents
    Everything from a draft or a proposal, through acceptance/rejection, to publication and supplies links to copies of publications
  The Metro-Haul web site provides links to all OA publications
    The pages are auto-generated from the Eurescom Document Tracker to allow the public to find our publications

## Slide 8: Open Access and Metro-Haul
We take this very seriously
  It is a requirement of the Grant Agreement
  We personally believe that all publicly funded research should be available
The project had a very bad start
  Publications take a long time to become available
  Project processes were not working
  At Year One review we had only 10 OA articles in Eurescom and none in ECAS
    Reviewers and Project Officer rightly highlighted this
Started to pick up at 18 months
  Project Officer pointed us at ECAS (we were focused on Eurescom)
  ECAS reached 34 papers (c. 30%)
  Eurescom reached about 70 papers (c. 60%)
It is hard work for Metro-Haul with roughly 260 disseminations and deliverables to date
  Victims of our own success!
Year Two figures follow on a later slide

## Slide 9: How we are Tracking Open Access in SyGMa (was ECAS)
This is the formal tracking of project publications
  Only shows published/presented materials
    Draft, Submitted, Accepted are not included
  DOI is a requirement for all journal articles
  DOI not required for…
    Conference presentations
    Standards contributions
  Clickable links present Repository or Open Access versions of the publications
Type of publication
Journal article (must have been published)
Conference proceedings (must have been published)
Conference material (must have been presented)
Standards contribution (includes opensource)
Project deliverable (must have been approved)
Open access venue
Publisher’s site
OpenAire or Zenodo repository
Stable institutional OA site with pointer from OpenAire or Zenodo
ResearchGate with open
download
ResearchGate with “copy-on-request”
BSCW /pub/ open repository
Personal sites, or partner sites
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A

## Slide 10: Tracking Open Access in Eurescom Document Tracker
Items entered into Eurescom Document Tracker show up automatically on the project web site
  https://metro-haul.eu/publications/research-papers/
  Clickable links present Open Access versions of the publications
  Our objectives…
    Make as much material as possible visible
    Bridge the gap until formal OA is available
Type of publication
Journal article (must have been published)
Conference proceedings (must have been published)
Conference material (must have been presented)
Standards contribution (includes opensource)
Project deliverable (must have been approved)
Open access venue
Publisher’s site
OpenAire or Zenodo repository
Stable institutional OA site with pointer from OpenAire or Zenodo
ResearchGate with open
download
ResearchGate with “copy-on-request”
BSCW /pub/ open repository
Personal sites, or partner sites
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A

## Slide 11: Open Access Numbers
Numbers can be confused by many disseminations in Draft, Submitted, Accepted, and Rejected states
  Qualifying publications are those in “published” state
  Qualifying deliverables are those that are approved by the Commission and “public”
  Qualifying standards are contributions to an open SDO
  Qualifying conference contributions have been delivered (presented)
Numbers will improve as more publications become available
 | Total in any state | Total qualifying | Eurescom/Website OA | SyGMa OA
Publications and Proceedings | 69 | 62 | 61 (98%) | 42 (68%)
Deliverables | 26 | 5 | 5 (100%) | 5 (100%)
Standards | 18 | 9 | 9 (100%) | 9 (100%)
Conference presentations | 149 | 97 | 84 (87%) | 55 (57%)
Totals | 262 | 173 | 159 (92%) | 111 (64%)

## Slide 12: WP6 – Key Achievements in Year 2 (1 of 5)
Notable WP6 success in Year 2 includes:
  Disseminations
    During the second year of the Project, METRO-HAUL has produced more than 100 dissemination activities.
    These are a combination of peer-reviewed papers and journals, articles, standards, and OpenSource contributions
  Journal Publications
    16 Highly ranked publications
  Conferences & Workshop Participation
    Participated at 12 industry and academic events
    Produced more than 70 contributions (see table)
Conference Participation | Year 1 | Year 2 | Total
EUCNC | 1 | 1 | 2
European Conference on Optical Communications (ECOC) | 10 | 12 | 22
International Conference on Transparent Optical Networks (ICTON) | 11 | 28 | 39
Layer123 - Zero Touch and Carrier Automation Conference 2018 |  | 1 | 1
Layer123 SDN NFV World Congress | 1 | 1 | 2
Optical Fiber Communications Conference and Exhibition (OFC) 2019 |  | 20 | 20
OSA Advanced Photonics Congress 2018 |  | 1 | 1
IEEE International Multidisciplinary Conference on Engineering Technology, IMCET 2018 |  | 1 | 1
IEEE NFV-SDN 2018 |  | 1 | 1
Conference on Optical Network Design and Modelling (ONDM) |  | 4 | 4
Other conferences | 7 | 2 | 9
TOTAL | 30 | 72 | 102

## Slide 13: WP6 – Key Achievements in Year 2 (2 of 5)
Why is Standardisation and OpenSource Important?
  Impact extends to vendors and operators outside the project in Europe and around the world
    It is open and publicly visible
  Standard architectures
    Enable all vendors to work with same objectives
    Allow operators to build coherent systems
  Standard data models
    Allow vendor implementations to interwork
    Free operators from “vendor lock-in”
  OpenSource implementations
    Provide staring point for consistent implementations
    Offer proof-of-concept
    Enable validation of implementations as “standard”
  Recognition of Metro-Haul (and thus European Commission) as leaders
Benefits for Metro-Haul partners (i.e., European companies)
  Shape the standards/OpenSource to fit needs of partners
  Early view (pre-standard implementation)
Metro-Haul Standardisation and OpenSource Impact
  12 Active SDO Specification and Standards Contributions
  Multiple Open Source code contributions (WP4 and WP5 discussions earlier)

## Slide 14: WP6 – Key Achievements in Year 2 (3 of 5)
Two External Project Workshops led by Metro-Haul
  May 2019 - NGON Workshop
    “The Optical Masterclass Series – METRO-HAUL”
      Reached out beyond H2020 projects
      Speakers from operators, equipment vendors, standards experts, and YANG implementers to explain how key technologies can provide everything needed to manage and operate packet and optical transport networks for 5G.
  June 2019 - EUCNC Workshop
    “Photonic Technologies in 5G and Beyond”
      Highlighted of Metro-Haul research and the impact of photonic integrated devices and optical for 5G.
Numerous, Keynotes, Invited & Accepted Speakers, Panels, Tutorials, Demonstrations and Exhibitions
  ECOC 2018
  PSC2018
  5GPPP KPI 2018
  OFC2019
  ICTON 2019
  ONDM 2019

## Slide 15: WP6 – Key Achievements in Year 2 (4 of 5)
  OFC Participation
    At OFC 2019 we had over 20 contributions and speaking slots
  Publication of project Newsletters
    Two Published
  Press Releases
    Four Released
  Blogs
    17 Technical and Project Blogs published on our website
  Industry Dissemination
    Light Reading Website Article
    Light Reading Video Interview
  YouTube Channel
    ECOC 2018 Demo on Automated End-to-End Carrier Ethernet Provisioning over a Disaggregated WDM (156 views)
    ECOC 2018 - Demonstration of Automated Carrier Ethernet across Disaggregated WDM Metro Network (130 views)
    METRO-HAUL: The Essential Infrastructure for an End-to-End Viable 5G Solution" at ITU Forum (61 views)
    Fully Disaggregated ROADM White Box Demo (471 views)

## Slide 16: WP6 – Key Achievements in Year 2 (5 of 5)
5G-PPP Participation
  Architecture Working Group
    Metro-Haul Champions: Infinera, Bristol Uni, CTTC Barcelona
  Software (was SDN & NFV)
    Champions: CTTC Barcelona, Bristol Uni, ODC
  5G Trials
    Champions: Telefonica TID, Bristol Uni, ADVA Germany
  Pre-standards
    Champions: ODC
  Automotive
    Champions: Eindhoven TU/e, OLC
5G-PPP Participation Output
  Cloud-Native and Verticals’ Services Whitepaper (drafted in Year 2, published September 2019)
  Revised Architecture Whitepaper ver3.0 (June 2019)
  were developed in Year 1, and reviewed and published in Year 2 in the Euro 5G-PPP Annual Journal (May 2019)
Golden Nuggets

## Slide 17: WP6 – Website & Social Statistics
  Top content pages in year 2 included:
    https://metro-haul.eu/2018/08/23/network-slicing-at-the-ietf/
    https://metro-haul.eu/2018/09/11/net2plan-hackathon-report/
    https://metro-haul.eu/2018/08/30/what-is-actn/
    https://metro-haul.eu/event/ecoc-2018/
  The /Publications/ pages are ranked in top 10, including “Research papers” page
    This continues to underline that visitors check METRO-HAUL research outcomes
  The Blog, Events, and News areas also gain good visibility
  Website visitors from around the world
    Europe, then USA, Canada, South America and Asia. India also features a high access
  Website Statistics, Year 2 versus Year 1
    Users up 140% - 2,604 users in Year 2, versus 1,085 Users in Year 1
    Organic search for website up 317% in Year 2
    Direct traffic up 44% in Year 2

## Slide 18: Social Media
Social Media Statistics
  Twitter
    303 Followers in Year 2, versus 142 Followers in Year 1
    >500 Tweets in Year 2, versus >200 in Year 1
  Research Gate Project Page
    >65 Followers
    >480 Reads)
  LinkedIn
  YouTube
    6 videos

## Slide 19: WP6 – Innovation Management
Already discussed this morning
  Just a reminder
The innovation results, emerged thus far and disclosed, are extremely compelling and demonstrate an auspicious trend for the project
The Innovation report is public and can be found at:
  https://bscw.metro-haul.eu/pub/bscw.cgi/d47157/InnovationManagement_2Audit.pdf
International patent filings have begun, or patent applications are currently pending. Some ideas and patents have been provided to project partners with FRAND terms.
Innovative project software has also been made available within the project partner consortium as “open software”, and in most of the cases loaded in specialised hardware and shared in several demonstrators

## Slide 20: WP6 – Issues Identified from Year 1 and Actions Taken in Year 2
Open Access to dissemination very poor
  Resolved misunderstanding about requirements
  Considerable progress made
  More work needed
Novelty of Innovation unknown
  Clarifications added to this year’s Innovation Report
No newsletter in Year 1
  Two newsletter published in Year 2
Need closer participation with 5G-PPP and H2020 projects
  Much greater involvement with 5G-PPP in Year 2
  Held joint workshop with other projects at EUCNC
Project blog under-used and poor disseminated
  Very successful increase in blogging in Year 2 with many partners involved
  Blogs being read quite widely
YouTube channel under-used
  Gradual increase in available videos during Year 2
  Good number of viewings
Assess publication and conference quality/impact
  Want to measure our dissemination better
  Action still needed
Academic outreach status unknown
  Action still needed

## Slide 21: WP6 – Actions for Year 3
Open Access
  Good progress in Year 2, but more to be done
  Target periodic activities to improve figures:
    Chase partners at each plenary for audit of all dissemination activities
    Quarterly survey of all Open Access sources by WP6 leadership
  Work out how to handle dissemination published after end of project
Assess publication and conference quality/impact
  Want to measure our dissemination better
  Need to qualify publications and conferences by reputation and size
Academic outreach status unknown
  Work with academic partners to determine ways to reach other institutions
Durability of Metro-Haul output
  Planning for end of project…
    How can the website content persist?
    How can we collate and preserve the dissemination material?

## Slide 22: Questions or Clarifications?
http://metro-haul.eu
Adrian Farrel - adrian@olddog.co.uk
Old Dog Consulting